## CR 4.0.8 & 4.0.9
SITEC - CHANGE REQUEST POINTS
S. NO | Version | CR.No. | Module Type | Module | Screen | Summary | Pupose | View | Comments | Corrective Action | Status
1 | 4.0.8 | LIMS/4.0.8/CR/0001 | Transaction | Registration | Sample Registration | QA level approval required instead of QC |  | link
2 | 4.0.8 | LIMS/4.0.8/CR/0002 | Transaction | Registration | Generic Registration | QA level approval required instead of QC
3 | 4.0.8 | LIMS/4.0.8/CR/0003 | Transaction | Registration | Protocol Registration | QA level approval required instead of QC
4 | 4.0.8 | LIMS/4.0.8/CR/0004 | Transaction | Registration | Instrument Scheduler | QA level approval required instead of QC
5 | 4.0.8 | LIMS/4.0.8/CR/0005 | Transaction | Registration | Sample Registration | Approval flow needs to be change like Checker --> SH --> QA --> HO |  | link | All Step's Screenshot Need
6 | 4.0.8 | LIMS/4.0.8/CR/0006 | Transaction | Registration | Generic Registration | Approval flow needs to be change like Checker --> SH --> QA --> HO |  | link
7 | 4.0.8 | LIMS/4.0.8/CR/0007 | Transaction | Registration | Study Allocation | Approval flow needs to be change like SH --> QA |  | link
8 | 4.0.8 | LIMS/4.0.8/CR/0008 | Transaction | Registration | STF Approval | Approval flow needs to be change like Checker --> SH --> QA |  | link
9 | 4.0.9 | LIMS/4.0.9/CR/0001 | Transaction | Registration | Sample Registration | The "Contact person" field should be made mandatory in pre-registration screen. |  | link | old and new screenshot need | Old and New screenshot added | Done
10 | 4.0.9 | LIMS/4.0.9/CR/0022 | Transaction | Registration | Generic Registration | Client Name, Address and Intimation (attachment), a field for Container ID, test count fields added in material for category standards for Working Standard, Test Standard in Pre- registration. |  | link | Need to check remaining terms
11 | 4.0.9 | LIMS/4.0.9/CR/0025 | Transaction | Registration | Sample Registration | In sample registration if we add the new test it can't able to add if "Subgroup" or "Test group" name contain single quotes. |  | link | DONE |  | Done
12 | 4.0.9 | LIMS/4.0.9/CR/0002 | Transaction | Result Entry | Result Entry By Sample | There should be a provision of 'Sample log report' button in 'Result Entry by Sample' Screen to the user level as Analyst. |  | link | Done |  | Done
13 | 4.0.9 | LIMS/4.0.9/CR/0003 | Transaction | Quotation & Invoice | Invoice Approval | The Invoice which are "Approved" and Sample which are “Authorized & Released” on previous day will get export on SAP server at 00:00 hrs in .tsv format. The file name should be in “SITECARD_YYYYMMDD.tsv”. |  | Client side | Done |  | Done
14 | 4.0.9 | LIMS/4.0.9/CR/0004 | Transaction | Quotation & Invoice | Invoice | There should be a provision to select the 'Currency' in 'Edit Invoice Entry' Window, A new screen for Currency to be added with add, edit, delete and Export options in Master |  | link | Done |  | Done
15 | 4.0.9 | LIMS/4.0.9/CR/0005 | Transaction | Quotation & Invoice | Invoice Approval | Invoice Approval, new approval level to be added in the Invoice approval Flow i.e "Accounts" as Verifier |  | Bug | Account or Accounts Need the Proper flow demonstration From Mr.Amit
16 | 4.0.9 | LIMS/4.0.9/CR/0020 | Transaction | Quotation & Invoice | Invoice | Working standard COA also go for Invoicing |  | Bug
17 | 4.0.9 | LIMS/4.0.9/CR/0014 | Transaction | Material Management | Standards | Assay and purity column globally added in the all the labels with standard format |  | link | Different slides
18 | 4.0.9 | LIMS/4.0.9/CR/0015 | Transaction | Material Management | Standards | In Outside party standards label, Standard no. value is changed from Reference No. to Standard Inventory No. |  | link
19 | 4.0.9 | LIMS/4.0.9/CR/0016 | Transaction | Material Management | Standards | For all labels the Direction of use, purity and assay details and name of standard, due to letters space is limited restriction is fixed so that complete details are reflected on label print. |  | link | Fixed in both version, Maximum Length of Each Term
20 | 4.0.9 | LIMS/4.0.9/CR/0017 | Transaction | Material Management | Standards | Direction of use column is removed and Assay,purity details are added to the Analytical Standards 's Label |  | link | Seperate screenshots
21 | 4.0.9 | LIMS/4.0.9/CR/0018 | Transaction | Material Management | Standards | Reference standard Batch No. details are added in list for lot checking |  | NA | Probably fixed in both version
22 | 4.0.9 | LIMS/4.0.9/CR/0019 | Transaction | Material Management | Standards | Storage condition is mentioned on Reference standard label |  | link | Different slides
23 | 4.0.9 | LIMS/4.0.9/CR/0021 | Transaction | Material Management | Standards | Expiry date of Reference standards to be edited even if release the material inventory. |  | link | Seperate screenshots
24 | 4.0.9 | LIMS/4.0.9/CR/0024 | Transaction | Material Management | Standards | The four-digit Standard No is generated for the corresponding record in Material Module. |  | link | Seperate screenshots
25 | 4.0.9 | LIMS/4.0.9/CR/0027 | Transaction | Material Management | Standards | Index issue in standard module. In the earlier version, After the record is added or edited in the popup screen, When user submit and close the popup screen The edited record or added record was not highlighted properly rather it highlights and select the first record. This issue has been fixed in the 4.0.9 version where the cursor will highlight the exact record which was added or edited |  | link | TBC in 4.0.7 | Checked in 4.0.7, It working properly | Done
26 | 4.0.9 | LIMS/4.0.9/CR/0026 | Transaction | Scheduler | Instrument Scheduler | In instrument scheduler if the user made a correction it will add as new record in the scheduler detail instead of updating the corresponding record. |  | link | Fixed in both version
27 | 4.0.9 | LIMS/4.0.9/CR/0006 | Master | User Management | User Account Approval | A filter button is to be added for sorting of user requests by using Request Type, User Name, Instrument Name, Software name options. |  | link | Seperate screenshots
28 | 4.0.9 | LIMS/4.0.9/CR/0007 | Master | User Management | Login | Unlock User button needs to be added on Login page for user to send the unlock user request. |  | link | Seperate screenshots
29 | 4.0.9 | LIMS/4.0.9/CR/0023 | Master | User Management | User Account Approval | Director QA approval replaced by Head Operation QA approval for User Request. |  | link | Exact Role name for HOQA and Site admin | 1.HO QA, DQA Name is entered 2. Site Admin is same | Done
30 | 4.0.9 | LIMS/4.0.9/CR/0008 | Master | User Management | User Request | Need to add tooltip for Director QA approval / Site Admin Approval column to view the Approval / Rejection comment given by Director QA / Site Admin |  | link
31 | 4.0.9 | LIMS/4.0.9/CR/0009 | Master | User Management | Audit Trail | Audit trail should be sorted according to date column. |  | link | 2-3 months Record sort (Need to Test)
32 | 4.0.9 | LIMS/4.0.9/CR/0013 | Transaction | Material Management | Standards | Test standards: Vial label Type B added. |  | link | Correct screenshot for Type A, Type B selection
33 | 4.0.9 | LIMS/4.0.9/CR/0012 | Transaction | Material Management | Standards | Outside party standards: Vial label Type B added. |  | link
34 | 4.0.9 | LIMS/4.0.9/CR/0010 | Master | User Management | Audit Trail | Need to filter audit trail using Module Name, Form Name and User Name. |  | link

## 4.0.7
SITEC - CHANGE REQUEST POINTS
S. NO | Version | CR.No. | Module Type | Module | Screen | Summary | Status
1 | 4.0.7 | LIMS/4.0.7/CR/0001 | Transaction | Stabilty | Study Allocation | Schedule pullout date should be schedule date in report | Delievered in 4.0.7
2 | 4.0.7 | LIMS/4.0.7/CR/0001.1 | Transaction | Stabilty | Study Allocation | Intermediate schedule shall always be started after the scheduled pullout dates in the scheduler, as it is an intermediate condition | Delievered in 4.0.7
3 | 4.0.7 | LIMS/4.0.7/CR/0004 | Transaction | Stability | STF Approval | Product specific validation for Type-3 : In this case, New table having the list of product that needs to be printed through the new CIPLA template. | Delievered in 4.0.7
4 | 4.0.7 | LIMS/4.0.7/CR/0005 | Transaction | Stability | STF Approval | STF Approval UI Change Request The STF approval screen will allow the user to approve the Stability ARNO which then printed as STF report. | Delievered in 4.0.7
5 | 4.0.7 | LIMS/4.0.7/CR/0006 | Transaction | Stability | STF Approval | By default tests under ‘Results’ tab should be selected. | Delievered in 4.0.7
6 | 4.0.7 | LIMS/4.0.7/CR/0007 | Transaction | Stability | STF Approval | STF Report generation should reflect test based on tests selection under ‘Results’ tab. (Batch no., Study Time point, Storage Condition, AR No. should get auto selected as per existing system) | TBD
7 | 4.0.7 | LIMS/4.0.7/CR/0008 | Transaction | Stability | STF Approval | STF Comments will not be pulled in intermediate screen & will remain as it is but validation for locking edit comments will be removed and thus, STF Comments will remain open for edit for Checker, Reviewer and Verifier even after Approval | Delievered in 4.0.7
8 | 4.0.7 | LIMS/4.0.7/CR/0009 | Transaction | Stability | STF Approval | User (Checker/ reviewer or Verifier) will thus do edit comment just before STF print, will do test selection as per client need and print STF report. Updated STF comment will appear on STF and changes done will get audit trailed.-For editing the comments in already verified STF. | Delievered in 4.0.7
9 | 4.0.7 | LIMS/4.0.7/CR/0010 | Transaction | Stability | STF Approval | STF comments section validation- any user who has the control rights access will able to update the STF comments.remove the validation for the STF comments | Delievered in 4.0.7
10 | 4.0.7 | LIMS/4.0.7/CR/0011 | Transaction | Stability | STF Approval | Enable E-signature for the STF comment where users needs to key in the credentials along with the reason that gets saved in audit trail (note: This E-sign will pop-up for both first time entry or during Edit as have only one control button “Add STF Comments” where we can add/update STF comments) | Delievered in 4.0.7
11 | 4.0.7 | LIMS/4.0.7/CR/0014 | Transaction | Approval | Approval | Address Changes in COA | Delievered in 4.0.7
12 | 4.0.7 | LIMS/4.0.7/CR/0012 | Transaction | Stability | STF Approval | STF comments can be updated any time and the last saved comments will appear in the STF report during the release. | Delievered in 4.0.7
13 | 4.0.7 | LIMS/4.0.7/CR/0002 | Transaction | Approval | Approval | There should be provision in LIMS to mark particular COA as ‘Manual’ and user should be able to attach PDF copy of manually prepared COA against the same and the same should be available to download and view/ print whenever required. The same provision needs to be made in ‘Archive transactions’ since the record may get archived. | Hold
14 | 4.0.7 | LIMS/4.0.7/CR/0003 | Master | User Management | User Account Approval | LIMS Site Admin/ Admin Request approval Site Admin and Site Admin user request is going for HO QA approval. | Delievered in 4.0.7

## CR - Client (hidden)
SITEC - CHANGE REQUEST POINTS
S. NO | Version | CR.No. | Module Type | Module | Screen | Summary | Pupose
1 | 4.0.8 | LIMS/4.0.8/CR/0001 | Transaction | Registration | Sample Registration | QA level approval required instead of QC
2 | 4.0.8 | LIMS/4.0.8/CR/0002 | Transaction | Registration | Generic Registration | QA level approval required instead of QC
3 | 4.0.8 | LIMS/4.0.8/CR/0003 | Transaction | Registration | Protocol Registration | QA level approval required instead of QC
4 | 4.0.8 | LIMS/4.0.8/CR/0004 | Transaction | Registration | Instrument Scheduler | QA level approval required instead of QC
5 | 4.0.8 | LIMS/4.0.8/CR/0005 | Transaction | Registration | Sample Registration | Approval flow needs to be change like Checker --> SH --> QA --> HO
6 | 4.0.8 | LIMS/4.0.8/CR/0006 | Transaction | Registration | Generic Registration | Approval flow needs to be change like Checker --> SH --> QA --> HO
7 | 4.0.8 | LIMS/4.0.8/CR/0007 | Transaction | Registration | Study Allocation | Approval flow needs to be change like SH --> QA
8 | 4.0.8 | LIMS/4.0.8/CR/0008 | Transaction | Registration | STF Approval | Approval flow needs to be change like Checker --> SH --> QA
9 | 4.0.9 | LIMS/4.0.9/CR/0001 | Transaction | Registration | Sample Registration | The "Contact person" field should be made mandatory in pre-registration screen.
10 | 4.0.9 | LIMS/4.0.9/CR/0002 | Transaction | Result Entry | Result Entry By Sample | There should be a provision of 'Sample log report' button in 'Result Entry by Sample' Screen to the user level as Analyst.
11 | 4.0.9 | LIMS/4.0.9/CR/0003 | Transaction | Quotation & Invoice | Invoice Approval | The Invoice which are "Approved" and Sample which are “Authorized & Released” on previous day will get export on SAP server at 00:00 hrs in .tsv format. The file name should be in “SITECARD_YYYYMMDD.tsv”.
12 | 4.0.9 | LIMS/4.0.9/CR/0004 | Transaction | Quotation & Invoice | Invoice | There should be a provision to select the 'Currency' in 'Edit Invoice Entry' Window.
13 | 4.0.9 | LIMS/4.0.9/CR/0005 | Transaction | Quotation & Invoice | Invoice Approval | Invoice Approval, new approval level to be added in the Invoice approval Flow i.e "Accounts" as Verifier.
14 | 4.0.9 | LIMS/4.0.9/CR/0006 | Master | User Management | User Account Approval | A filter button is to be added for sorting of user requests by using Request Type, User Name, Instrument Name, Software name options.
15 | 4.0.9 | LIMS/4.0.9/CR/0007 | Master | User Management | Login | Unlock User button needs to be added on Login page for user to send the unlock user request.
16 | 4.0.9 | LIMS/4.0.9/CR/0008 | Master | User Management | User Request | Need to add tooltip for Director QA approval / Site Admin Approval column to view the Approval / Rejection comment given by Director QA / Site Admin
17 | 4.0.9 | LIMS/4.0.9/CR/0009 | Master | User Management | Audit Trail | Audit trail should be sorted according to date column.
18 | 4.0.9 | LIMS/4.0.9/CR/0010 | Master | User Management | Audit Trail | Need to filter audit trail using Module Name, Form Name and User Name.
19 | 4.0.9 | LIMS/4.0.9/CR/0011 | Master | Quotation & Invoice | Invoice | A new screen for Currency to be added with add, edit, delete and Export options.